## Slide 1
Uttarakhand Public Works Dept.
Contractual Obligations, Functions , Claims&
Disputes
Two Days Work shop on
Contract Management
5-6 January 2024 Dehradun
Dr. Sridhar Mothe

## Slide 2: Principles of Project Management
Management is an art of getting the things done by the people as per the objectives through the system , process
Management is an Art and Science both
Functions of management : Planning , Organizing , Staffing , Directing
Controlling , Reporting , Budgeting ( POSDCORB)
Project Management principles for Construction ( Finance , materials , machinery etc.)
Construction project is on product sold and made analogy
Management of Construction and Construction management
Construction projects are executed through Contracts

## Slide 3: Some Aspects of Contract Administration
Contract Administration as a separate discipline as Project Management
Administration Vs Management Difference in Approaches
Contract --- A legally enforceable Agreement
having legal implications , creating obligations
Generating Rights , Defining Duties
Emanating from good practices , approaches followed by experienced field
Engineers ‘Contract Administration’ is emerging as a discipline which is a
blend of technical and legal subjects
All Contracts are governed by Indian Contract Act 1872 .

## Slide 4
Contractual Obligations
On performance of a duty as an obligation right is generate
Employer's Obligations :
    Handing Over site, work fronts
    Supply of Agreed materials in time
    Issue of drawings
    Decisions , Approvals
    Deliver agreed facilities
    Timely payments as per agreed terms
Contractor’s obligations : Timely execution, Quality , progress etc
  EOT , Limitation periods specified if any in agreement on intimations
  On hinderance , Occurance of Extra items , deviations
  Dispute notifications
Cond…

## Slide 5
Correspondence
Correspondence is one of the most important requirement of good Contract Administration.
Types of Correspondence - Necessary , Obligatory , General
Some Tips
Correspondence be brief, to the point with brevity
With decency , decorum and official sense
No circastic remarks , critical comments , no personal
With relevant references
Body of the letter is important – what is the issue what
one intends to communicate or put it on record
No Narrative and lengthy
Simple language , simple sentences
Language effects and Style
Simple Arts of letter writing
Cond…

## Slide 6
Maintenance of Records
Evidence of hindrances ( Correspondence files, Minutes of meetings, Site diaries : Documentation of events))
Site Records ( registers) and documentation ( Photos, Videos, Reports)
Drawing registers
Day work sheets / Daily reports
Hindrance Register
Variation regsiters
Site order book
Materials register
Manpower , Plant & Machinery deployment register
Cond…

## Slide 7
Other Functions of Contract Manager
Conversant with applicable taxes , taxation issues
Applicable technical specifications for work
Billing and Quantity surveying
Analysis of rates , variations valuations
Periodic communications , reporting ( MIS)
Resources planning , Progress monitoring , controlling
Budgeting and Quality control aspects
Laws applicable for Construction contracts
Statutory Compliance aspects

## Slide 8
Types of Contracts :
Different types of contracts :
Item rate , Percentage rate
EPC , LS / Turnkey
Design & Build
Cost Plus
BOOT , BOT (PPP)
Reverse Auctioning and Swiss challenge

## Slide 9
Risk and Variation Management
In Item rate Contracts – Proper estimation of Quantities , Items incorporation
& Percentage Rate - Deviation Limit
- Extra Items scope valuations
- Proper Investigations ( Preliminary , Soil)
- Planning / Preliminary Design
EPC , LS / Turnkey - Defining the Scope , Valuation methods for Out of scope
( Technical Parameters , Specifications )
Design & Build - Design Data , design Specifications , Parameters
Cost Plus - Less Risky but proves costly if not monitored and
controlled
BOOT , BOT
Reverse Auctioning and Swiss challenge

## Slide 10: Claims and Disputes
Claims in Construction Contracts are inevitable
Indian Construction Industry is facing Litigations of around Rs. One Lakh Crores
Each year Ministry of Statistics and Program implementation publishes data of Projects of value
> 150 Cr.
84% Projects are undergoing time , cost over runs
In 70 % cases of disputes State is a party to litigation

## Slide 11: Anatomy of Disputes
Major chunk of disputes are delay claims / prolongation costs
LDs, EOT related issues
Extra items , rate differences
Quantum meruit cases and valuations
Damages for contractual defaults
Ambiguities and Interpretations related issues
Untenable recoveries , withholds , payment defaults

## Slide 12: Claims and Substantiation
It is easy to lodge a Claim and equally difficult to substantiate it
As per Civil Law burden of proof lies with Claimant
Substantiation is based on contemporaneous records and documentation
Good contract administration during execution and good practices right from commencement
Time and performance aspects are neglected by both parties and taken in casual manner

## Slide 13: Claims and Substantiation
In many cases proper plan / practicable base line program is absent
Though scheduling / monitoring softwares are used not effective in practice
Estimation of resources ( manpower, machinery and materials) and their management is a big challenge
Industry is facing shortage of skilled manpower at all levels

## Slide 14
Types of Claims
Contractual Claims.
Extra Contractual Claims.
Quantum Merit Claim.
Ex-gratia Claims.
Counter Claims.
Notes: 14

## Slide 15
1. Contractual Claims :- Claims which arise put of the express provision of the particular contract i.e., for Extra Cost, Expense and direct loss specifically provided as a remedy in contract.
2.Extra-Contractual Claims :- also called as Common law claims. These are for damages for breach of contract at common law.
3.Quantum Merit Claims:-Provides remedy for a person who has carried out work under the instruction of the owner but no price has been agreed
4. Ex-gratia Claims :- Ex-gratia claim is one where no legal remedy is available to the Contractor but arise out of hardship. These Claims are also called sympathy claims and are considered on mercy and moral liability.
5.Counter Claims: These claims are raised by the opposite party to counter the claims of the claimant.
Notes: 15

## Slide 16
Substantiation of claims
Substantiation of claims is a tedious and difficult task.
The onus of substantiation of proofs/justification of the claim lies on the claimant ie whoever put forth the claims.
Good record keeping ,maintenance of records, evidences through correspondence , preservation of related record is necessary for sustaining a claim.
In case of delay claims ,proofs and evidences on various hindrances ,delays are required with good periodic correspondence with the client.
In idling /under-utilization claims, resources like manpower and machinery deployed in a particular period are required for record building.
Need to check for limitation clause for lodging any claim
The parties cannot alter any legal provisions i.e. limitations, their law rules by mutual agreement.
Notes: 16

## Slide 17: Disputes arise from Claims
Potential Causes of Disputes :
Delays in handing over of site, work fronts.
Variation in data/information supplied and that actually encountered during execution
Late supply of drawings, decisions, approvals
Disruption/disturbance caused due to untimely or unjustified instructions.
Employers defaults affecting performance like delayed payments, illegal recoveries etc. Ambiguities persisting in Terms
Deviations , variations beyond agreement provisions , change in scope
Non approval of justified rates for Variations , extra scope works
Violation of Contract conditions , stipulated and agreed provisions
Cond…

## Slide 18
Avoidance and Remedies
Planning is tedious, time consuming , complex
Appreciation of Planning function
Correct and optimum Planning right from conception to completion
Unambiguous , fair , workable conditions
Avoidance of poor drafting
No cut paste methods
Practicable specs , norms, standards
Sharing of risks , responsibilities in execution
Fair Contract Administration
Harmonious working relations
Viewing the other party as a resource to get the work done
Good Communication , no cults
Discussions , Amicable settlements
Cond…

## Slide 19
Avoidance and Remedies
Planning before floating tenders
Planning is important function at tender stage which is not given proper
Attention
Reasons being lack of time , lack of resources , easy taking
Proper planning from dept . While framing estimate , NIT
Adequate technical investigation , site soil investigation , surveys
Adequate site trail pits , soil profile assessments based on size of plot,
Location of buildings
Preparation of BOQ incorporating relevant items of work with good
planning
Estimating correct quantities , rates for arriving reasonable cost estimate
Cond…

## Slide 20
Delay Claims in Construction Contracts
Delay is lateness
Disruption is impediment in planned , sequence of operations
( Resources are underutilized – less efficiently used –
lost productivity)
Four Cardinal Principles for Delay Claims substantiation
1) Cause of Delay
2) Delay Responsibility as per contract
3) Impact of Delay ( Suitable delay analysis )
4) Quantification ( Cost of the impact)
Seqenece

## Slide 21
Types of Delays and EOT issues :
Different types of Delays :
Compensable , Excusable Delay ( CD )
Excusable , No compensable Delay ( NCD )
Non Excusable Delay ( ND )
Concurrent Delays
Justification of Delays by Delay Analysis
Base line Program , Impact of Delays on Critical Paths
As Planned Method of delay analysis
As Built Methods of delay analysis

## Slide 22
Delay Analysis Methodologies and EOT ( UK SCL
Protocols) :
CPM Scheduled Based Delay Analysis Methodologies
As Planned Vs As Built Delay analysis
Impacted Planned Schedule Method
Collapsed As Built Methodology ( But for or Entitled )
Windows delay analysis methods
Time Impact Analysis
Suitability of methodology depends upon many criterion
UK Society of Construction Law ( SCL 2003 ) has published Delay analysis , EOT protocols ( Four basic principles as guide lines- Records maintenance , Program , EOT,
Delay Analysis methodology to be agreed. ( Revised SCL Protocols 2017) .

## Slide 23
Delay Claims Assessment methods :
Actual Cost Method ( Classification of Costs in time , non time related in extended period that is fixed costs and variable costs)
Total Cost Method ( Comparison of As bid costs with total incurred costs in actual executed period – difference )
Modified Total Cost Method ( Discounted )
Jury Verdict Method
When no other quantification is possible Tribunal can come at reasonable equitable adjustment for cost compensation when there is clear proof of injury ( No reliable method possible to be proved)
Global / Composite Claims discouraged

## Slide 24
Typical Heads of Recovery
Machinery , Equipment
Manpower
Site Overheads ( General , Site office)
Head office Over Heads ( HOOH)
( Formulae based assessment : Hudson, Emden , Eichley )
Interest , Finance Charges
Insurance , BG Costs
Loss of profit

## Slide 25
Quantum Meruit / Cost Claims :
Contractual Valuation for Extra / Out of Scope works
Escalation Provisions
Variations / deviations and Limits of applicability
Commercial Viabilities , Differences in rate derivations
Quantum Meruit – no quantification agreed
Industry practices , market rate evaluations etc.

## Slide 26
Evidence :
Strict Rules of Evidence and Evidence Act are not applicable for Arbitration ( Sec-19 )
However AT is to follow general principles of evidence
AT can decide admissibility of evidence, relevance and weight of evidence
Evidence Types
- Oral , Documentary
- Direct , Hear Say
- Primary
- Secondary
Generally in Construction / Infrastructure disputes site records and correspondence
exchanged is produced as documentary evidence ( Exhibits)
MoMs , bill copies , registers , progress reports etc.

## Slide 27
Limitation :
Law of limitation deals with time limits for enforcing the rights
Perpetual nature of litigations not bound by time do create unrest and disharmony in
society
Normally in Construction disputes for claims the time period of limitation is 3 years
from Cause of action with in which legal redress to be made
Because of this limitation is a mix of law and based on facts
Limitation periods are specified in Statutes wherever applicable
After Limitation right is not extinguished but claim is time barred as not enforceable
By agreement terms Statutory limitation can’t be suppressed or altered

## Slide 28
Important Issues :
Whether Time is Essence of any Contract which is normally regarded
Hind Construction Contractors Vs State of Maharashtra ( SC 1979)
Section - 55 of Indian Contract Act Provisions
Hindrances and Valid extension of time , Third party delays
Provisional Extension of Time
Liquidated Damages ( Genuinely Estimated, Pre agreed ) and Penalty
Undertakings and No Claim certificates
Fixed Price and Price adjustable contracts
Breach of Contract , Damages ( section -73, 74, 75)

## Slide 29
Important Issues :
Force Majure Provisions ( Act of God) : Meaning Superior Strength
Industry Norms , Contract provisions
Impact on Construction Industry , Lock downs, Releif Measures by Govt.
Novation : Substitution of existing contract with new one ( Section-62 of Contract act)
Delay Claims and Substantiation
Four Cardinal Principles : 1) Cause of Delay
2) Responsibility as per contract
3) Impact of Delay ( Suitable delay analysis )
4) Quantification

## Slide 30
Important Issues :
Excepted matters ( These are the terms restricting the scope of legal
remedy like putting a bar on adjudication to Arbitration on certain
determination by Engineer like EOT , Extra item sanction etc. )
Such exempted issues are called Excepted matters as excluded from
Adjudication / Arbitration
Fundamental Breach , Substantial Breach , Material Breach
Termination of contract ( Contractual , Legal)
Suspension
Discharge

## Slide 31
Settlement of Disputes :
Dispute avoidance and settlement is the present buzz word
Courts are also obligated to explore settlement under Sec-89 of
CPC and encourage parties before admitting case
Court annexed ADR centers are becoming popular
NHAI has constituted a three member CGM committee to see
and recommend to board evolving settlement mechanism of disputes
even when matters are before Arbitral tribunal
Internally policy frame work and guide lines with roles ,
responsibilities can be worked out in Dept.

## Slide 32
Thank You
Notes: 32